## Work Plan
Ref. | Work Package / Activity | Leader/Main Ps | Other Ps involved | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
WP1 | Project Management | P1 | USC | bar: M1; M13; M19; M25; M37 to M48
1.1 | Kick-off meeting | P1 | All partners | bar: M2
1.2 | Financial management and administration | P1 | All partners | [48 empty] | Progress as originally planned
1.3 | Project internal communication and coordination | P1 | All partners | [48 empty] | In progress with delay
1.4 | 2nd Management meeting | P4 | All partners | bar: M25; M28
1.5 | 3rd Management meeting | P3 | All partners | [48 empty] | Completed as originally planned | bar: M42
WP2 | Preparation | P2 | Ayeconomics | [48 empty] | Completed with delay | bar: M1; M13; M19; M25; M37 to M48
2.1 | Development of guidelines for target group survey | P2 | bar: M1 to M3
2.2 | Implementation of Workshops/Survey with stakeholders (3 per HEI) | CA partners | [49 empty] | Event/milestone | bar: M4 to M11
2.3 | Analysis of needs and competences | P2 | CA partners | bar: M5 to M12
2.4 | Analysis of international master programs | P1, P3, P4 | [49 empty] | Delayed start | bar: M2 to M17
2.5 | Accounting and monitoring mechanisms | P1 | bar: M1 to M4
2.6 | Project’s implementation plan | P1 | [49 empty] | Postponed/Temporarily suspended | bar: M1 to M5
2.7 | Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs) | All partners | bar: M2 to M3
WP3 | Development | P1, P10 | bar: M1; M13; M19; M25; M37 to M48
3.1 | Curriculum design and preparation | bar: M1; M13; M19; M25; M37 to M48
3.1.1 | Development of the curriculum for the Master Program | All partners | bar: M6 to M16
3.1.2 | Curriculum presentation to stakeholders | P6, P9 and P11 | CA partners | bar: M23
3.1.3 | Content development | P1 | All partners | bar: M13 to M25
3.1.4 | Developing of English language training program and Improving English proficiency of academic staff | P5 | CA partners | bar: M2 to M26
3.1.5 | Trainings on the Master subjects | P2, P1, P3, P4 | CA partners | bar: M25 to M28
3.1.6 | Certification and accreditation process | CA partners | bar: M16 to M41
3.2 | Entrepreneurs Centres | P9 | bar: M1; M13; M19; M25; M37 to M48
3.2.1 | Training on the Establishment of Entrepreneurs Centres | P1, P9 | CA partners | bar: M25
3.2.2 | Establishment of Entrepreneurs Centres | CA partners | bar: M25 to M33
3.2.3 | Coordination of Entrepreneurs | CA partners | bar: M34 to M45
3.3 | Master Programme implementation | bar: M1; M13; M19; M25; M37 to M48
3.3.1 | Student enrolment procedure | CA partners | bar: M29 to M32; M41 to M44
3.3.2 | Full implementation | P1 | CA partners | bar: M32 to M42
3.3.3 | Follow-up reports | P5,7,8,9,10,11 | bar: M37 to M42
3.3.4 | Follow-up meeting | P1 | All partners | bar: M42
3.3.5 | Content update | P1 | All partners | bar: M43 to M45
3.4 | Sustainability and Long-term recommendations | P11 | All partners | bar: M1; M13; M19; M25; M37 to M48
3.4.1 | Methodology | P11 | All partners | bar: M6 to M9; M21 to M26
3.4.2 | Implementation | P11 | All partners | bar: M34 to M48
3.4.3 | Report and recommendations | P11 | All partners | bar: M44 to M48
WP4 | Quality Assurance | P1, P11 | bar: M1; M13; M19; M25; M37 to M48
4.1 | Quality Plan | P1, P5, P11 | All partners
4.2 | Periodical reports | P11 | All partners | bar: M13; M25; M37; M45
WP5 | Dissemination | P6 | bar: M1; M13; M19; M25; M37 to M48
5.1 | Developing dissemination strategy | P6 | All partners
5.2 | Development of professional network | CA partners | bar: M3 to M6; M22 to M48
5.3 | Promotion of the Master Programme | All partners | bar: M29; M45
5.4 | Web site and visual identity | P4, P6
5.5 | Social media and communication | P4
5.6 | Articles and publications | All partners
5.7 | Dissemination, promotional campaigns, info and open days | CA partners
Note on F3: Online Kick-off meeting
Note on J4: 1st reporting period
Note on P4: 2nd reporting period
Note on V4: 3rd reporting period + Intermediate report (EACEA)
Note on AB4: 4th reporting period
Note on AH4: 5th reporting period
Note on AN4: 6th reporting period
Note on AT4: 7th reporting period
Note on AZ4: Final reporting
Note on I5: Internal Communication & Coordination Plan
Note on AC6: 2nd management meeting at USC (Part 1)
Note on AF6: 2nd management meeting (Part 2)
Note on AT7: 3rd management meeting at UL
Note on AA19: Dunshabe, Ashbad and Karaganda
Note on AC22: Face to Face - Part 1 Santiago de Compostela
Note on AD22: Online trainings
Note on AE22: Online trainings
Note on AF22: Face to Face - Part 2
Note on AC25: 1 day training provided by ECBP at USC
Note on AT32: During the management meeting at UL
Note on J39: Presentation of the Quality Plan
Note on Q39: Final Quality Plan
Note on Q40: 1st periodical report
Note on AC40: 2nd periodical report
Note on AO40: 3rd periodical report
Note on AW40: 4th periodical report
Note on G42: Presentation of the final Dissemination Strategy
Note on AG44: Visit of EU partners fro promotion workshop
Note on AW44: Visit of EU partners fro promotion workshop
Note on J45: Presentation of the website
Note on J46: Creation of social media accounts

## Outputs
Ref. | Work Package / Activity | Responsible | Format | Comments | Publication? | Status | Start | End | Comments
WP1 | Project Management | P1
1.1 | Kick-off meeting | P1 |  |  |  | Done | 2020-03-12 | 2020-03-13
| Agenda | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-03-05
| Attendance list | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-03-27
| Minutes | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-03-24
| Presentations | All partners | Presentation (.pdf, .pptx, .odp) | Use project template | Internal | Done |  | 2020-03-13
| Photos | P1 | Image (.jpg, .png) |  | Public | Done |  | 2020-03-13
1.2 | Financial management and administration | P1 |  |  |  | In progress | 2020-01-15 | 2023-01-14
| Reporting templates | P1 | Documents and spreadsheets (.docx, .xlsx) | Use EACEA templates (JD, TS, ITR, etc.) | Internal | Done |  | 2020-03-13
| Financial Management Guide | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-06-29
| Individual expenditure reports (every 6 months) | All partners | Scanned documents (.pdf) | Signed/stamped reporting templates (JD, TS, ITR) and supporting documents (invoices, tickets, boarding cards, bank statements) | Internal | In progress
| 1st year consolidated report | P1 | Spreadsheet (.xlsx, .ods) | Compiled by the coordinator | Internal | Done |  | 2021-04-30
| 2nd year consolidated report | P1 | Spreadsheet (.xlsx, .ods) | Compiled by the coordinator | Internal
| 3rd year consolidated report | P1 | Spreadsheet (.xlsx, .ods) | Compiled by the coordinator | Internal
1.3 | Project internal communication and coordination | P1 |  |  |  | In progress | 2020-01-15 | 2023-01-14
| Internal Communication and Coordination Plan | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-05-22
| Set up communication channels | P1 | Online Resources |  | Internal | Done |  | 2020-03-30
| Set up online project repository | P1 | Online Resource | Google Drive | Internal | Done |  | 2020-03-30
| Internal progress reports | All partners | Document (.pdf, .docx, .odf) |  | Internal | In progress
1.4 | 2nd Management meeting | P4
| Agenda | P4, P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Attendance list | P4 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Minutes | P4, P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations | All partners | Presentation (.pdf, .pptx, .odp) | Use project template | Internal
| Photos | P4 | Image (.jpg, .png) |  | Public
1.5 | 3rd Management meeting | P3
| Agenda | P3, P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Attendance list | P3 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Minutes | P3, P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations | All partners | Presentation (.pdf, .pptx, .odp) | Use project template | Internal
| Photos | P3 | Image (.jpg, .png) |  | Public
WP2 | Preparation | P2
2.1 | Development of guidelines for target group survey | P2 |  |  |  | Done | 2020-01-15 | 2020-01-30
| Survey guidelines | P2 | Document (.pdf, .docx, .odf) | Use project template | Public | Done |  | 2020-01-30
| 1st round survey of the Delphi analysis | P2 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-01-30
| 2nd round survey of Delphi analysis | P2 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-01-30
| Survey for the identification of skill needs | P2 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-10-08
2.2 | Implementation of Workshops/Survey with stakeholders (3 per HEI) | CA partners |  |  |  | Done | 2020-01-30 | 2020-12-15
| Survey responses | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public | Pending |  | 2020-12-15
| Workshop programs | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-06-26 | TJ not carried out
| Workshop attendance lists & report | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal | Pending |  | 2020-06-26 | TJ not carried out
| Workshop presentations | CA partners | Presentation (.pdf, .pptx, .odp) | Use project template | Internal | Done |  | 2020-06-26 | TJ not carried out
| Workshop photos | CA partners | Image (.jpg, .png) |  | Public | Done |  | 2020-06-26 | TJ not carried out
2.3 | Analysis of needs and competences | P2 |  |  |  | Done | 2020-01-30 | 2021-01-07
| Market Needs Analysis Report | P2 | Document (.pdf, .docx, .odf) | Use project template | Public | Done |  | 2021-01-07
| Competence Analysis Report | P2 | Document (.pdf, .docx, .odf) | Use project template | Public | Done |  | 2020-10-26
| Summary of results infographics | P2 | Document (.pdf, .docx, .odf) | Use of project logo and Eramus+ visibility | Public | Done |  | 2020-10-26
2.4 | Analysis of international master programs | P1, P3, P4 |  |  |  |  | 2020-02-16 | 2021-06-05
| Report on the analyisis of international master programs | P1, P3, P4 | Document (.pdf, .docx, .odf) | Use project template | Public | Done |  | 2021-06-05
2.5 | Accounting and monitoring mechanisms | P1 |  |  |  |  | 2020-01-15 | 2020-05-18
| Budget expenditure and achievement indicator spreadsheets | P1 | Spreadsheet (.xlsx, .ods) | Updated regularly | Internal | Done |  | 2020-05-18
2.6 | Project’s implementation plan | P1 |  |  |  |  | 2020-01-15 | 2020-06-05
| Implementation Plan | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal | Done |  | 2020-06-05
| Work Plan (calendar, roles and responsibilies, outputs) | P1 | Spreadsheet (.xlsx, .ods) | Updated regularly | Internal | In progress
2.7 | Defining Management Board, Dissemination board (DB), Academic Board (AB), Entrepreneurship Centre Manager (ECM), Task Core Groups (TCGs) | All partners |  |  |  |  | 2020-03-12 | 2020-04-06
| Compostition of the Boards | All partners | Spreadsheet (.xlsx, .ods) |  | Internal | Done |  | 2020-04-06
WP3 | Development | P1, P10
3.1 | Curriculum design and preparation
3.1.1 | Development of the curriculum for the Master Program | All partners |  |  |  | In progress | 2021-01-07
| Developed and approved Master Program Curriculum | All partners | Document (.pdf, .docx, .odf) | Use project template | Public | Done |  | 2021-04-21
| Local meetings agenda | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Local meetings minutes | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Local meetings attendance lists | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Local meetings photos | CA partners | Image (.jpg, .png) |  | Public
3.1.2 | Curriculum presentation to stakeholders | P6, P9 and P11
| Worshops agenda | P6, P9, P11 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Workshops attendance list | P6, P9, P11 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Workshops report | P6, P9, P11 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Workshop presentations | P6, P9, P11 | Presentation (.pdf, .pptx, .odp) | Use project template | Public
| Workshop Photos | P6, P9, P11 | Image (.jpg, .png) |  | Public
3.1.3 | Content development | P1 |  |  |  |  | 2021-04-21
| Developed and approved course materials (online and offline) | P1 | Document (.pdf, .docx, .odf) + Online Resources | Use project template | Public | In progress
3.1.4 | Developing of English language training program and Improving English proficiency of academic staff | P5 |  |  |  |  | 2020-02-15 | 2022-03-01
| List of trainees | P5 | Document (.pdf, .docx, .odf) + Online Resources | Use project template | Internal | In progress |  | 2020-04-30
| Report on the outcomes of the English training program | P5 | Document (.pdf, .docx, .odf) + Online Resources | Use project template | Internal | In progress
3.1.5 | Trainings on the Master subjects | P2, P1, P3, P4
| Training programs and agendas | P2, P1, P3, P4 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Attendance lists | P2, P1, P3, P4 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Training reports | P2, P1, P3, P4 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations/Training materials | P2, P1, P3, P4 | Presentation (.pdf, .pptx, .odp) | Use project template | Public
| Photos | P2, P1, P3, P4 | Image (.jpg, .png) |  | Public
3.1.6 | Certification and accreditation process | CA partners
| Accreditation process report | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Official certification and accreditaion documentation | CA partners | Document (.pdf) |  | Internal
3.2 | Entrepreneurs Centres | P9
3.2.1 | Training on the Establishment of Entrepreneurs Centres | P1, P9
| Training program and agenda | P1, P9 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Attendance lists | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Training reports | P1, P9 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations/Training materials | P1, P9 | Presentation (.pdf, .pptx, .odp) | Use project template | Public
| Photos | P1 | Image (.jpg, .png) |  | Public
3.2.2 | Establishment of Entrepreneurs Centres | CA partners
| Handbook on the establishment of Entreprenuer Centres | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
| Report on the established Entreprenuer Centres | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
3.2.3 | Coordination of Entrepreneurs | CA partners
| Programs and agendas of the seminars | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
| Attendace lists | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations/Training materials | CA partners | Presentation (.pdf, .pptx, .odp) | Use project template | Public
| Photos | CA partners | Image (.jpg, .png) |  | Public
3.3 | Master Programme implementation
3.3.1 | Student enrolment procedure | CA partners
| Publication of marketing and educational materials | CA partners |  |  | Public
| Report on the enrolment procedure | CA partners |  |  | Internal
3.3.2 | Full implementation | P1
| Feedback Analysis | P1 | Document (.pdf, .docx, .odf) + Online Resources | Use project template | Internal
3.3.3 | Follow-up reports | P5,7,8,9,10,11
| Follow-up reports | P5,7,8,9,10,11 | Document (.pdf, .docx, .odf) | Use project template | Public
3.3.4 | Follow-up meeting | P1
| Agenda | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Attendance list | P3, P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Minutes | P1 | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations | All partners | Presentation (.pdf, .pptx, .odp) | Use project template | Internal
| Photos | P3, P1 | Image (.jpg, .png) |  | Public
3.3.5 | Content update | P1
| Report on Master content update |  | Document (.pdf, .docx, .odf) | Use project template | Public
3.4 | Sustainability and Long-term recommendations | P11
3.4.1 | Methodology | P11
| Sustainability Strategy | P11 | Document (.pdf, .docx, .odf) | Use project template | Public
3.4.2 | Implementation | P11
| Sustainability Strategy Implementation Plan | P11 | Document (.pdf, .docx, .odf) | Use project template | Internal
3.4.3 | Report and recommendations | P11
| Sustainability Strategy: Report and recommendations | P11 | Document (.pdf, .docx, .odf) | Use project template | Public
WP4 | Quality Assurance | P1, P11
4.1 | Quality Plan | P1, P5, P11 |  |  |  |  | 2020-01-15 | 2023-01-14
| Quality Plan | P1, P5, P11 |  |  | Public | Done | 2020-05-20 | 2021-02-09
| External Evaluation interim and final evaluation reports | P1 |  |  | Internal
4.2 | Periodical reports | P11
| Periodical reports (1 per year) | P11 |  |  | Internal
WP5 | Dissemination | P6
5.1 | Developing dissemination strategy | P6 |  |  |  |  | 2020-01-15 | 2023-01-14
| Dissemination Strategy | P6 | Document (.pdf, .docx, .odf) | Use project template | Public | Done | 2020-01-15 | 2020-04-04
| Dissemination reports | P6 | Document (.pdf, .docx, .odf) | Use project template | Internal | In progress |  |  | 1st year report completed
5.2 | Development of professional network | CA partners
| Report on the development of the professional network | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
5.3 | Promotion of the Master Programme | All partners
| Meetings Agenda | All partners | Document (.pdf, .docx, .odf) | Use project template | Public
| Attendance list | All partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Minutes | All partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Presentations | All partners | Presentation (.pdf, .pptx, .odp) | Use project template | Public
| Photos | All partners | Image (.jpg, .png) |  | Public
5.4 | Web site and visual identity | P4, P6 |  |  |  |  | 2020-01-15 | 2023-01-14
| Project website | P4 | Online Resourece |  | Public | Done | 2020-01-15 | 2020-05-30 | Regularly updated
| Project logo | P6 | Image (.jpg, .png) |  | Public | Done | 2020-01-15 | 2020-03-30
5.5 | Social media and communication | P4 |  |  |  |  | 2020-01-15 | 2023-01-14
| Set up social media channels | P4 | Online Resourece |  | Public | Done | 2020-01-15 | 2020-05-30 | Regularly updated
5.6 | Articles and publications | All partners
| 2 articles published by partner | All partners | Document (.pdf, .docx, .odf) / Online Resources |  | Public
5.7 | Dissemination, promotional campaigns, info and open days | CA partners
| Dissemination and promotional materials for the campaigns | CA partners | Documents and online resources |  | Public
| Open Days Agendas | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
| Open Days Attendance lists | CA partners | Document (.pdf, .docx, .odf) | Use project template | Internal
| Open Days Presentations | CA partners | Document (.pdf, .docx, .odf) | Use project template | Public
| Photos | CA partners | Presentation (.pdf, .pptx, .odp) | Use project template | Public
Note on F1: Public: Can be made available to the general public through the relevant mediums (i.e. project website) Internal: Available for project Partners and the EACEA.